## Sheet1
Work Item Type | Title | Parent
Epic | Inventory Management System
Feature | 1. Database Architecture & Setup | Inventory Management System
Feature | 2. Web App Development | Inventory Management System
Feature | 3. Backend Integration with Azure SQL | Inventory Management System
Feature | 4. Inventory Logging & Loss Tracking | Inventory Management System
Feature | 5. QR Code System | Inventory Management System
Feature | 6. Deployment to Azure | Inventory Management System
Feature | 7. Reporting & Analytics | Inventory Management System
Feature | 8. Offline Support & Syncing | Inventory Management System
User Story | Set up project database | 1. Database Architecture & Setup
Task | Design ERD for Events, Inventory, EventInventory | Set up project database
Task | Define primary/foreign keys and relationships | Set up project database
Task | Write SQL scripts to create schema | Set up project database
User Story | Deploy Azure SQL database | 1. Database Architecture & Setup
Task | Create Azure SQL Server | Deploy Azure SQL database
Task | Create Azure SQL Database | Deploy Azure SQL database
Task | Configure firewall and access | Deploy Azure SQL database
Task | Test connection from local machine | Deploy Azure SQL database
User Story | Build inventory tracking UI | 2. Web App Development
Task | Build form for manual item selection | Build inventory tracking UI
Task | Build quantity input for used/lost | Build inventory tracking UI
Task | Add event metadata input | Build inventory tracking UI
User Story | Display current inventory | 2. Web App Development
Task | Fetch inventory from database | Display current inventory
Task | Show item availability | Display current inventory
User Story | Enable database connection | 3. Backend Integration with Azure SQL
Task | Configure pyodbc or SQLAlchemy | Enable database connection
Task | Store credentials securely | Enable database connection
User Story | Implement data operations | 3. Backend Integration with Azure SQL
Task | Insert new events | Implement data operations
Task | Insert/update inventory | Implement data operations
Task | Log item usage per event | Implement data operations